| P.O.S Web App |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| Scope | Stack | Timeline | Budget |
| --- | --- | --- | --- |
| Full System | Web-based | 8–10 Weeks | $500 USD |

Project Overview:

This proposal outlines the scope, deliverables, timeline, and cost for implementing a web-based Point of Sale (POS) system. The system covers four core modules — Company, Product, Sales, and Administration — providing end-to-end management of customers, inventory, invoicing, and user access controls. This proposal was prepared for the Client on May 21, 2026.

Delivery Phases (Scope & Timeline):

| Phase # | Phase | Duration | Status |
| --- | --- | --- | --- |
| 1 | Setup & Configuration | 1 week | $500 Total |
|  | - Project setup and initial system preference |  |  |
| 2 | Module 1 & 2 Development | 2–3 weeks |  |
|  | - Module 1 — Company: Customer management (add, edit, history), customer types and segmentation, customer receipts and payment recording, sales person management, and ledger/receivables reports. |  |  |
|  | - Module 2 — Product: Product categories/sub-categories, product catalogue with barcode support, stock locations, UOM configuration, and all stock reports (summary, current stock, ledger, re-order level, barcode printing). |  |  |
| 3 | Module 3 & 4 Development | 2–3 weeks |  |
|  | - Module 3 — Sales: Sale orders, invoices (including VAT), returns, and sale/return register reports. |  |  |
|  | - Module 4 — Administration: Multi-branch support, user accounts and role-based access rights, bulk import of products/customers (Excel/CSV), and user activity/active user/users list reports. |  |  |
| 4 | Testing, Review, & Go-Live | 2–3 weeks |  |
|  | - Integration testing & bug fixes (1–2 weeks). |  |  |
|  | - Client review & revisions (1 week). |  |  |
|  | - Go-live & training (1 week). |  |  |

| Budget Breakdown |  |  | Cost |
| --- | --- | --- | --- |
|  |  | Total Estimated Duration | 8–10 Weeks |
|  |  | TOTAL | $500 USD |

What You Receive (Deliverables):

- Fully configured POS system: All 4 modules live and functional.

- User documentation: Based on the provided requirements doc.

- User accounts & roles: Admin and staff roles configured.

- Bulk import templates: Excel/CSV templates for products & customers.

- Training walkthrough: One remote session (up to 1 hour).

- Post-launch support: 30 days bug-fix support after go-live.

Terms & Conditions:

- 50% advance payment required to commence work; 50% on delivery.

- Scope is limited to the features described in this proposal. Any additions will be quoted separately.

- Client is responsible for hosting, domain, and server costs.

- Source code and all deliverables are transferred to the client upon final payment.

Acceptance:

To proceed, please confirm your acceptance of this proposal in writing. Work will begin upon receipt of the advance payment.